## ProjectSchedule
INDENTIFICAÇÃO ÚNICA DE USUÁRIO | [14 empty] | ► Watch How to Make a Gantt Chart in Excel
Equipe 3 |  | Project Start: | 2021-08-30 |  |  | Orçamento: | 21000
Tabatha Fróes |  | Today: | 2021-10-09 |  |  | Valor restante: | 10510.875
|  | Display Week: | 1 | [10 empty] | 2021-08-30 | [6 empty] | 2021-09-06 | [6 empty] | 2021-09-13 | [6 empty] | 2021-09-20 | [6 empty] | 2021-09-27 | [6 empty] | 2021-10-04 | [6 empty] | 2021-10-11 | [6 empty] | 2021-10-18
 | time axis 2021-08-30 to 2021-10-24
TAREFA | ATRIBUÍDO PARA | PROGRESSO | INÍCIO | TÉRMINO PLANEJADO | TÉRMINO REALIZADO | DIAS PLANEJADOS | DIAS REALIZADOS | CUSTO POR HORA | HORAS PLANEJADAS | HORAS REALIZADAS | CUSTO PLANEJADO | CUSTO REALIZADO | DIAS | time axis 2021-08-30 to 2021-10-24
Sprint 1 - Windows | Integrantes |  | 2021-08-30 | 2021-09-19 | 2021-09-19 | [6 empty] | 5131 | 21
[BACK - BD] Conexão com o Banco de Dados | Tábatha Fróes | 100% | 2021-09-06 | 2021-09-06 | 2021-09-06 | 1 | 1 | 16.29 | 4 | 4 | 65.16 | 65.16 | 1
[FRONT] Criação da Tela de Cadastro | Matheus Rothstein | 100% | 2021-09-06 | 2021-09-08 | 2021-09-09 | 3 | 4 | 13.64 | 12 | 16 | 163.68 | 218.24 | 3
[BACK] Método Cadastro | José Henrique dos Santos | 100% | 2021-09-10 | 2021-09-11 | 2021-09-12 | 2 | 3 | 13.64 | 8 | 12 | 109.12 | 163.68 | 2
[FRONT] Captação dos Dados de Entropia do Usuário | Matheus Rothstein e Ângelo Lima | 100% | 2021-09-10 | 2021-09-18 | 2021-09-18 | 9 | 9 | 13.64 | 36 | 36 | 491.04 | 491.04
[BD] Configuração e Modelagem do Banco | Renato Passos | 100% | 2021-09-03 | 2021-09-04 | 2021-09-05 | 2 | 3 | 13.64 | 8 | 12 | 109.12 | 163.68 | 2
[BD] Dicionário de Dados | Renato Passos | 100% | 2021-09-14 | 2021-09-19 | 2021-09-19 | 6 | 6 | 13.64 | 24 | 24 | 327.36 | 327.36
[BACK] Criação do Hash para Usuários Únicos | Tabatha Fróes e Ângelo Lima | 100% | 2021-09-16 | 2021-09-19 | 2021-09-16 | 4 | 1 | 29.93 | 16 | 4 | 478.88 | 119.72
[BACK] Score de Pontuação dos Usuários Inicial | José Henrique dos Santos | 100% | 2021-09-13 | 2021-09-18 | 2021-09-18 | 6 | 6 | 13.64 | 24 | 24 | 327.36 | 327.36
[BACK] Identificação Device Fingerprint | Ângelo Lima | 100% | 2021-09-18 | 2021-09-19 | 2021-09-18 | 2 | 1 | 13.64 | 8 | 4 | 109.12 | 54.56
[BACK] Método Exibir Usuários com ID Único | José Henrique dos Santos | 100% | 2021-09-15 | 2021-09-19 | 2021-09-19 | 5 | 5 | 13.64 | 20 | 20 | 272.8 | 272.8
[DOC] Documentação Geral 1/4 | Larissa Takahashi e Natália Neves | 100% | 2021-09-05 | 2021-09-19 | 2021-09-19 | 15 | 15 | 48.79 | 60 | 60 | 2927.4 | 2927.4 | 15
Sprint 2 - Linux | Integrantes |  | 2021-09-20 | 2021-10-10 | 2021-10-10 | [6 empty] | 5358.125 | 21 | bar: 2021-09-20 to 2021-10-10
[FRONT] Criação da Tela de Cadastro | Matheus Rothstein | 0% | 2021-09-22 | 2021-09-29 | 2021-09-28 | 8 | 7 | 13.64 | 32 | 28 | 436.48 | 381.92 | 8
[BACK] Validações e regras de negócio | Ângelo Lima | 0% | 2021-09-22 | 2021-09-29 | 2021-09-29 | 8 | 8 | 13.64 | 32 | 32 | 436.48 | 436.48 | 8
[BACK] Exibição dos Usuários | Tabatha Fróes | 0% | 2021-09-29 | 2021-10-06 | 2021-10-07 | 8 | 9 | 16.29 | 32 | 36 | 521.28 | 586.44 | 8
[BACK] Integração entre o front-end, back-end e banco de dados | José Henrique dos Santos | 0% | 2021-09-22 | 2021-10-06 | 2021-10-06 | 15 | 15 | 13.64 | 60 | 60 | 818.4 | 818.4
[IA] Criação da IA | Caíque | 0% | 2021-09-22 | 2021-10-09 | 2021-10-08 | 18 | 17 | 13.64 | 18 | 17 | 245.52 | 231.88
[DOC] Documentação Geral 2/4 | Larissa Takahashi e Natália Neves | 0% | 2021-09-24 | 2021-10-10 | 2021-10-10 | 17 | 17 | 48.79 | 59.5 | 59.5 | 2903.005 | 2903.005 | 17
Sprint 3 - Android | Integrantes |  | 2021-10-18 | 2021-11-07 | 2021-11-07 | [7 empty] | 21
[FRONT] Comparações entre os dados de entropia e o hash | Ângelo Lima | 0%
[BACK] Método Cadastro | Tabatha Fróes | 0%
[BACK] Exibição dos Usuários com ID Único | Tabatha Fróes | 0%
[IA] Treinamento da IA com datasets | Renato Passos | 0%
[DOC] Documentação Geral 3/4 | Larissa Takahashi e Natália Neves | 0%
Sprint 4 - IOS | Integrantes |  | 2021-11-08 | 2021-11-28 | 2021-11-28 | [7 empty] | 21
[FRONT] Criação da Tela de Cadastro |  | 0%
[BACK] Método Cadastro |  | 0%
[FRONT] Método Identificação Device Fingerprint |  | 0%
[FRONT] Tela de Exibição dos Usuários com ID Único |  | 0%
[BACK] Método Rastreio Serial Number |  | 0%
[BACK] Método Rastreio IP |  | 0%
[BACK] Método Cruzar IP com SN |  | 0%
[BACK] Método Exibir Usuários com ID Único |  | 0%
[DOC] Documentação Geral 4/4 |  | 0%
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC

## Salários
Salário por Hora | Membros
16.29 | Tábatha Fróes
22.39 | Natália dos Reis Neves
26.4 | Larissa Takahashi
13.64 | Ângelo Lima
13.64 | Caique Fernandes
13.64 | José Henrique dos Santos
13.64 | Matheus Henrique Rothstein
13.64 | Renato Passos
13.64 | Sandro Toline

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
© 2018-2019 Vertex42 LLC
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
► Watch How This Gantt Chart Was Created
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.